## Sheet2
Yearly Plan 2023
Quarter: 1
Project: House price MVP with CI/CD
Week | Start | Sprint | ML deliverables | Frontend deliverables | Backend deliverables
Week 1 | 2023-01-02 | Sprint 1 | Define problem statement & set goals | Define problem statement & set goals | Define problem statement & set goals
Week 2 | 2023-01-09 |  | Gather and clean data | Create UI design and discuss functionalities | Estimate the needed infrastructure & set project credentials
Week 3 | 2023-01-16 |  | Setup github with CI | Setup project skeleton (framework, scripts) | Setup infrastructure with Terraform
Week 4 | 2023-01-23 |  | Build baseline model for benchmark | Setup github with CI | Setup project skeleton (framework, scripts)
Week 5 | 2023-01-30 | Sprint 2 | Build improved model (ridge regularization & gradient descent | Execute UI design and create functionalities | Design and deploy APIs
Week 6 | 2023-02-06 |  | Evaluate model based on RMSE and MAE scores | Execute UI design and create functionalities | Design and deploy APIs
Week 7 | 2023-02-13 |  | Select best fitting model & present results to stakeholders | Create unit tests & integration tests | Create unit tests & integration tests
Week 8 | 2023-02-20 |  | Deliver model to S3 location | Do end-to-end test | Do end-to-end test
Week 9 | 2023-02-27 | Sprint 3 | Setup CI process | Setup CI process | Setup CI process
Week 10 | 2023-03-06 |  | Setup CD process | Setup CD process | Setup CD process
Week 11 | 2023-03-13 |  | Leeway for delays | Leeway for delays | Leeway for delays
Week 12 | 2023-03-20 |  | Go-live date | Go-live date | Go-live date
Top Goals |  |  | Difficulty 1-3
ML | Deliver an ML model that is more accurate than the benchmark (lower RMSE and MAE) |  | 2
Frontend | Design user-friendly UI |  | 1
Backend | Use Infrastructure management & design APIs |  | 2

## Sheet1
Week | ML | Frontend | Backend
2023-01-02 | Define problem statement & set goals | Define problem statement & set goals | Define problem statement & set goals
2023-01-09 | Gather and clean data | Create UI design and discuss functionalities | Estimate the needed infrastructure & set project credentials
2023-01-16 | Setup github with CI | Setup project skeleton (framework, scripts) | Setup infrastructure with Terraform
2023-01-23 | Build baseline model for benchmark | Setup github with CI | Setup project skeleton (framework, scripts)
2023-01-30 | Build improved model (ridge regularization & gradient descent | Execute UI design and create functionalities | Design and deploy APIs
2023-02-06 | Evaluate model based on RMSE and MAE scores | Execute UI design and create functionalities | Design and deploy APIs
2023-02-13 | Select best fitting model & present results to stakeholders | Create unit tests & integration tests | Create unit tests & integration tests
2023-02-20 | Deliver model to S3 location | Do end-to-end test | Do end-to-end test
2023-02-27 | Setup CI process | Setup CI process | Setup CI process
2023-03-06 | Setup CD process | Setup CD process | Setup CD process
2023-03-13 | Leeway for delays | Leeway for delays | Leeway for delays
2023-03-20 | Go-live date | Go-live date | Go-live date
| Goals | Goals | Goals
| Deliver an ML model that is more accurate than the benchmark (lower RMSE and MAE) | Design user-friendly UI | Use Infrastructure management & design APIs
| Continuously improve model when new data is available | Use CI/CD pipelines | Use CI/CD pipelines
Difficulty indicators
Low
Medium
High